## Slide 1
14-10-2019
Tower-E Column Curing Up coming Task: Slab Casting will be on 17/10/2019
Status

## Slide 2
15-10-2019
Tower-G Plinth Beam Up coming Task: Slab Casting will be on 17/10/2019
Status

## Slide 3
15-10-2019
Tower-D Half slab casting done
Status

## Slide 4
15-10-2019
Tower-B Excavation done
Status

## Slide 5
15-10-2019
Tower-H Ground Floor slab casting done Up coming Task: First floor slab 18/10/2019
Status

## Slide 6
15-10-2019
Tower-C Soil filling in progress Up coming Task: Plinth beam casting
Status

## Slide 7
15-10-2019
Tower-A Reinforcement done for GF Slab Up coming Task: Slab Casting will be on 17/10/2019
Status

## Slide 8
15-10-2019
Tower-F First Floor slab casting done Up coming Task: SF column casting
Status